## scope and deliverables
Task | Objectives | Description
Project Scoping and Data cleaning | Determine the data required, obtain and clean the data | - Planning and setting up
- Document the scope of the project.
- Determine the parameters to be assessed and the data needed
- Establish the source of the data to be used in the model, quality, consistency and availability of the data
- Data mining: Obtain the data.
- Data cleaning: format it into data analytics format, adjust for outliers, missing data, ensure consistency in naming and labeling
Develop the Scoring model | Develop the scores that indicate the soundness of insurance companies. | - Determine possible segmentation (grouping based on time period, company characteristics e,g size, and any other existing grouping) of the data
: |  | - Determine the mathematical models/machine learning algorithms to be used in developing the score
- Develop the score/model/machine learning algorithm on python
- Includes testing model accuracy and validation
- Validation will be done by measuring the predictive accuracy of the model. 80% of the data is used to develop and train the model whereas 20% of the data is used to check how accurate the prediction is.
Automated Dynamic Data Visualization and Dashboarding | Develop end user graphs and tables that will always be displayed and used for decision making | - Determine the visual presentation of final analysis (what the end user will see and use e.g graphs, colour scheme for red flags, segmentations)
: |  | - Design the power bi dashboard
- Develop a means of automatically obtaining the data from the sources and loading the data into the model for assessment and reports generation.
- Develop the reports that will be generated for the end user
Testing, training, and deployment. | Train NCBA personnel on how to use and interpret the tool for decision making | - Train the user(s) that will be generating the reports using the models
- Explain how the model works, the algorithm used and interpretation
- Conduct test runs, of how the whole process will be conducted
The project will ensure the following
- Develop a score that categorizes insurance companies based on financial stability, liquidity and going concern.
- Develop a predictive insurance score
- Determine limits for premium financing business to individual insurance companies based on scores
- Develop an automated, dynamic Power Bi visualization that indicates the performance of individual insurance companies and flagging for companies that are a cause of concern
- Provide a write-up on the algorithm that generates the scores, assumptions and main considerations.
- Provide user training on the process of analysis and application of the scores

## sprints
sprint | main task | sub tasks | status | further description
1 | data gathering | collect balance sheet data for both gen and life insurane firms | in progress | data gathered is for only life insurance firms, still working on OCR converted statements
|  | collect P/L data for both gen and life insurane firms | in progress | data gathered is for only life insurance firms, still working on OCR converted statements
| fin ratio calculation | get gen insurance ratios | To do
|  | get life insurance ratios | To do